## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration
Feature | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
Homepage | 13 | 3 | 19 | 1 | 100 | bar: PERIODS 13
Login | 14 | 3 | 17 | 3 | 100
Logout | 15 | 1 | 19 | 1 | 100
Create Account | 16 | 4 | 16 | 4 | 100
Gantt Chart (MS2) | 15 | 5 | 15 | 1 | 100
Navigation Bar | 20 | 2 | 27 | 1 | 100
Sphinx | 18 | 2 | 19 | 1 | 100
Settings | 22 | 4 | 26 | 10 | 100
Meeting Page | 22 | 3 | 26 | 5 | 100
Guest Page (All parts) | 24 | 6 | 25 | 9 | 100
Gantt Chart (MS3) | 20 | 14 | 34 | 14 | 100