## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration
Feature | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Homepage | 1 | 3 | 7 | 1 | 100
Login | 2 | 3 | 5 | 3 | 100
Logout | 3 | 1 | 7 | 1 | 100
Create Account | 4 | 4 | 4 | 4 | 100
Gantt Chart | 3 | 5 | 3 | 1 | 100
Navigation Bar | 6 | 2 | 18
Sphinx | 6 | 2 | 7 | 1 | 100